ID

Project: BUS 119A Team 7 Date: Tue 5/7/19

Task Name Duration Work Start Finish

0

**BUS 119A Team 7 67 days 116 ... Mon 2/4/19Tue 5/7/19** 1

**Initiate 7 days 8 hrs Mon 2/4/19 Tue 2/12/19**

2

Meet with Sponser 1 day 4 hrs Mon 2/4/19 Mon 2/4/19

3

Write Team Charter 1 day 4 hrs Tue 2/12/19 Tue 2/12/19

4

**Plan 20 days 20 hrs Mon 2/4/19 Fri 3/1/19**

5

Define Project Requirments 1 day 4 hrs Mon 2/4/19 Mon 2/4/19

6

Develop project Charter 1 day 4 hrs Tue 2/5/19 Tue 2/5/19

7

1 day 4 hrs Tue 2/12/19 Tue 2/12/19

8

Create Project Schedule 1 day 4 hrs Tue 2/26/19 Wed 2/27/19

9

Meet with Sponser 1 day 4 hrs Fri 3/1/19 Fri 3/1/19

10

**Execute and Control 36 days 68 hrs Tue 3/5/19 Tue 4/23/19**

11

Implement item descriptions 1 day 4 hrs Tue 3/5/19 Tue 3/5/19

12

Create test data 1 day 4 hrs Thu 3/7/19 Thu 3/7/19

13

Test system 1 day 4 hrs Mon 3/11/19Mon 3/11/19

14

Wed 3/13/19 15

1 day 4 hrs Fri 3/15/19 Fri 3/15/19

16

Implement add item feature 1 day 4 hrs Mon 3/18/19Mon 3/18/19

17

Develop mobile compatibility 1 day 4 hrs Wed 3/20/19Wed 3/20/19

18

Test mobile compatibility 1 day 4 hrs Fri 3/22/19 Fri 3/22/19

19

Mon 3/25/19 20

Create reservation system 1 day 4 hrs Wed 3/27/19Wed 3/27/19

21

Create time management system 1 day 4 hrs Fri 3/29/19 Fri 3/29/19

22

1 day 4 hrs Mon 4/1/19 Mon 4/1/19

23

Demo system to sponsor 1 day 4 hrs Wed 4/3/19 Wed 4/3/19

24

Task Mode

Feb '19 Mar '19 Apr '19 May '19 Jun '19

Task

Split

20 27 3 10 17 24 3 10 17 24 31 7 14 21 28 5 12 19 26

Create & Revise Work Breakdown Structure

Implement user accounts/registration Implement check-in/checkout function/ column

Research time management syetm

Run system on Amazon Web Services

Final Test Sytem 1 day 4 hrs Mon 4/8/19 Mon 4/8/19

Milestone

Summary

Project Summary

Inactive Task

1 day 4 hrs Wed

3/13/19

1 day 4 hrs Mon

3/25/19

Inactive Milestone

Inactive Summary

Progress Manual Task

Duration-only

Manual Progress

Manual Summary Rollup

Manual Summary

Page 1

Start-only

Finish-only

External Tasks

External Milestone

Deadline

Baseline

**Project Manager,Analyst,Developer,Researcher**

**Researcher**

**Project Manager**

**Project Manager**

**Researcher**

**Researcher**

**Project Manager,Analyst,Developer,Researcher**

**Developer**

**Researcher**

**Researcher**

**Analyst**

**Developer**

**Researcher**

**Project Manager**

**Researcher**

**Researcher**

**Analyst**

**Developer**

**Project Manager**

**Project Manager Researcher**

Baseline Milestone

Baseline Summary

ID

Project: BUS 119A Team 7 Date: Tue 5/7/19

Task Name Duration Work Start Finish

25

**Control 36 days 12 hrs Tue 3/5/19 Tue 4/23/19**

26

Project Status Report 1 1 day 4 hrs Tue 3/5/19 Tue 3/5/19

27

Project Status Report 2 1 day 4 hrs Tue 3/26/19 Tue 3/26/19

28

Project Status Report 3 0.5 days 4 hrs Tue 4/23/19 Tue 4/23/19

29

**Close 5.06 days12 hrs Tue 4/30/19 Tue 5/7/19**

30

Finalize project presentation 0.5 days 4 hrs Tue 4/30/19 Tue 4/30/19

31

Finalize project binders 0.5 days 4 hrs Tue 5/7/19 Tue 5/7/19

32

Finalize SDLC binder 1 day 4 hrs Tue 5/7/19 Tue 5/7/19

33

**Evaluate Project 6 days 8 hrs Tue 4/30/19 Tue 5/7/19**

34

Peer Evaluation 1 day 4 hrs Tue 4/30/19 Tue 4/30/19

35

Task Mode

Feb '19 Mar '19 Apr '19 May '19 Jun '19

Task

Split

20 27 3 10 17 24 3 10 17 24 31 7 14 21 28 5 12 19 26

Submit lesson learned 1 day 4 hrs Tue 5/7/19 Tue 5/7/19

Milestone

Summary

Project Summary

Inactive Task

Inactive Milestone

Inactive Summary

Progress Manual Task

Duration-only

Manual Progress

Manual Summary Rollup

Manual Summary

Page 2

Start-only

Finish-only

External Tasks

External Milestone

Deadline

Baseline

**Project Manager**

**Project ManagerProject Manager**

Baseline Milestone

Baseline Summary

**Developer**

**Project Manager**

**Researcher**

**Analyst**

**Team**