ID

Project: scheduleRedo Date: Tue 5/7/19

Task Name Duration Start Finish

1

**Initiate 4 days Mon 2/4/19 Thu 2/7/19** 2

Meet with Sponsor 2 days Mon 2/4/19 Tue 2/5/19 3

Write Team Charter 2 days Wed 2/6/19 Thu 2/7/19 4

**Plan 14 days Fri 2/8/19 Wed 2/27/19** 5

Define Project Requirements 3 days Fri 2/8/19 Tue 2/12/19 6

Develop Project Charter 2 days Wed 2/13/19Thu 2/14/19 7

Create & Revise Work Breakdown Structure2 days Fri 2/15/19 Mon 2/18/19 8

Create Project Schedule 2 days Tue 2/19/19 Wed 2/20/19 9

Meet with Sponsor 3 days Thu 2/21/19 Mon 2/25/19 10

Reseach potential inventory solution 1 day Tue 2/26/19 Tue 2/26/19 11

Project Charter Signoff 1 day Wed 2/27/19Wed 2/27/19 12

**Execute and Control** 39 days? Thu 2/28/19 Tue 4/23/19 13

SDLC Phases 39 days? Thu 2/28/19 Tue 4/23/19 14

**Planning 4 days Thu 2/28/19 Tue 3/5/19** 15

Research transfer of admin right 1 day Thu 2/28/19 Thu 2/28/19 16

Research feasbility of alike items 1 day Fri 3/1/19 Fri 3/1/19 17

Research on server fesibility 2 days Mon 3/4/19 Tue 3/5/19 18

**Analysis 3 days Wed 3/6/19 Fri 3/8/19** 19

Analyze check-in check-out feasibility1 day Wed 3/6/19 Wed 3/6/19 20

Analyze QR code implementation 1 day Thu 3/7/19 Thu 3/7/19 21

Analyze reservation feasbility 1 day Fri 3/8/19 Fri 3/8/19 22

**Design 3 days Thu 3/14/19 Mon 3/18/19** 23

Task Mode

Feb '19 Mar '19 Apr '19 May '19

Task

Split

27 3 10 17 24 3 10 17 24 31 7 14 21 28 5 12

Create demo data 1 day Wed 3/13/19Wed 3/13/19

Milestone

Summary

Project Summary

Inactive Task

Inactive Milestone

Inactive Summary

Manual Task

Duration-only

Manual Summary Rollup

Manual Summary

Progress Start-only

Finish-only

Manual Progress

Page 1

External Tasks

External Milestone

Deadline

Critical

Critical Split

**All**

**All**

**All**

**Nick**

**Bill,Jaspreet**

**Wen,Jaspreet**

**All**

**Bill**

**Wen**

**Bill**

**Wen**

**Nick**

**Nick**

**Wen**

**Jaspreet**

**Bill**

ID

Project: scheduleRedo Date: Tue 5/7/19

Task Name Duration Start Finish

24

Test demo data 1 day Thu 3/14/19 Thu 3/14/19 25

Demo system to sponsor 1 day Fri 3/15/19 Fri 3/15/19 26

Implement 3 days Fri 3/22/19 Tue 3/26/19 27

Implement column attribute 1 day Fri 3/22/19 Fri 3/22/19 28

Implement QR method 1 day Mon 3/25/19Mon 3/25/19 29

Implement account privileges 1 day Tue 3/26/19 Tue 3/26/19 30

Maintenance and Support 21 days Tue 3/26/19 Tue 4/23/19 31

Documentation 17 days Tue 3/26/19 Wed 4/17/19 32

Create record and generate bar-code2 days Wed 3/27/19Thu 3/28/19 33

Modify existing records 1 day Fri 3/29/19 Fri 3/29/19 34

Add/configure new column attributes 1 day Mon 4/1/19 Mon 4/1/19 35

Add additional user level attributes1 day Tue 4/2/19 Tue 4/2/19 36

Backup and restore databse 1 day Wed 4/3/19 Wed 4/3/19 37

Item reservation system 5 days Thu 4/4/19 Wed 4/10/19 38

Tutorial/Walk-through 4 days Thu 4/11/19 Tue 4/16/19 39

Subscription management 2 days Thu 4/18/19 Fri 4/19/19 40

Software customer support 2 days Mon 4/22/19Tue 4/23/19 41

Control 36 days Tue 3/5/19 Tue 4/23/19 42

Project Status Report 1 1 day Tue 3/5/19 Tue 3/5/19 43

Project Status Report 2 1 day Tue 3/26/19 Tue 3/26/19 44

Project Status Report 3 1 day Tue 4/23/19 Tue 4/23/19 45

Close 13 days Fri 4/19/19 Tue 5/7/19 46

Task Mode

Feb '19 Mar '19 Apr '19 May '19

Task

Split

27 3 10 17 24 3 10 17 24 31 7 14 21 28 5 12

Final presentation to sponsor 1 day Fri 4/26/19 Fri 4/26/19

Milestone

Summary

Project Summary

Inactive Task

Inactive Milestone

Inactive Summary

Manual Task

Duration-only

Manual Summary Rollup

Manual Summary

Progress Start-only

Finish-only

Manual Progress

Page 2

External Tasks

External Milestone

Deadline

Critical

Critical Split

**Nick**

**Bill**

**Nick,Jaspreet**

**Wen**

**Jaspreet Nick**

**Nick**

**Nick**

**Bill NickWen**

**Jaspreet BillNickWen**

**Jaspreet Nick**

**All**

ID

Project: scheduleRedo Date: Tue 5/7/19

Task Name Duration Start Finish

47

Finalize project presentation 8 days Fri 4/19/19 Tue 4/30/19 48

Finalize PLC binder 2 days Mon 5/6/19 Tue 5/7/19 49

Finalize SDLC binder 2 days Mon 5/6/19 Tue 5/7/19 50

Evaluate 6 days Tue 4/30/19 Tue 5/7/19 51

Peer evaluation 1 day Tue 4/30/19 Tue 4/30/19 52

Task Mode

Feb '19 Mar '19 Apr '19 May '19

Task

Split

27 3 10 17 24 3 10 17 24 31 7 14 21 28 5 12

Submit lessons learned 1 day Tue 5/7/19 Tue 5/7/19

Milestone

Summary

Project Summary

Inactive Task

Inactive Milestone

Inactive Summary

Manual Task

Duration-only

Manual Summary Rollup

Manual Summary

Progress Start-only

Finish-only

Manual Progress

Page 3

External Tasks

External Milestone

Deadline

Critical

Critical Split

**AllAll All**

**AllAll**