## Sheet1
SDLC Stage | Risk Description | Risk Likelihood (1-10) | Risk Impact (1-10) | Total Risk Severity | Contingency Plan
Implementation | (R/T) Lack of resources/support to host the project online | 6 | 10 | 60 | Use database locally. Limit to one computer. (IT - Bill)
Implementation | (T) Technology components aren't reliable | 6 | 9 | 54 | Restore database from back-up. (IT - Bill)
Planning/Analysis/Implementation | (T) Technology not fit for task/project | 4 | 10 | 40 | Contact project sponsor and project champion immediately to discuss next steps; investigate alternative technologies. (Dev- Bill)
All Stages | (D/R) System fails sponsor review | 4 | 10 | 40 | Notify project champion. (PM - Nick)
Planning/Analysis | (T) Learning curves of tech/processes lead to delays | 6 | 6 | 36 | Revise project schedule for minor delays; contact project sponsor and project champion for major delays. (PM - Nick)
Planning | (T) Certain requirements not attainable using chosen technology | 4 | 9 | 36 | Notify project champion and project sponsor. Use third-party solution to replace, if possible. (IT - Bill)
Implementation | (D/R) Design turns out to be infeasible | 6 | 6 | 36 | Notify project sponsor; consult project champion for next steps. (PM - Nick)
Implementation/Analysis | (T) Platform hard to maintain | 4 | 8 | 32 | Inform project sponsor of the possible difficulties. Confirm that documentation is robust. (A - Wen)
Planning/Implementation | (SS) Sponsor's desires are misinterpreted | 3 | 10 | 30 | Immediate in-person meeting sponsor and champion for resolution. (All)
All Stages | (C) Lack of communication between team and sponsor | 5 | 6 | 30 | Advise project champion, set up weekly communication assignment. (All)
Implementation | (D/R) Requirements are not met | 3 | 10 | 30 | Schedule team meeting, determine if situation can be rectified. Proceed accordingly. (PM - Nick)
Planning | (R/T) Poor estimates of effort required | 4 | 7 | 28 | Contact project champion; revise project schedule. (PM - Nick)
All Stages | (R/T) Deadlines are not met on time | 4 | 7 | 28 | Meet with sponsor and project champion; revise project schedule. (PM - Nick)
Implementation/Support | (T) Database becomes too big for the server | 3 | 9 | 27 | Buy additional hard drive storage (PM - Nick)
All Stages | (D/R) Failure to follow methodology | 3 | 8 | 24 | Review SDLC and PLC documentation. (All)
All Stages | (R/T) Budget is exceeded | 4 | 6 | 24 | Notify project champion and project sponsor. (PM - Nick)
All Stages | (D/R) Tasks are completed incorrectly | 4 | 6 | 24 | Schedule team meeting to review relevant tasks; review and revise schedule as needed. (PM - Nick)
Implementation | (T) Admin account becomes inaccessible | 2 | 10 | 20 | Contact relevant customer support/IT support. Notify project champion. (PM - Nick)
Planning/Implementation | (PS) Project timeline extended due to unknown application errors | 3 | 6 | 18 | Contact project champion and project sponsor for guidance. (PM - Nick)
All Stages | (SS) Sponsor become disengaged | 2 | 9 | 18 | Contact project champion immediately. (PM - Nick)
All Stages | (R/T) Scheduling errors | 3 | 6 | 18 | Contact project champion; review schedule. (PM - Nick)
Implementation | (PS) Project scope becomes inflated | 2 | 8 | 16 | Review project charter, remind team of project goals. (PM - Nick)
Implementation | (T) Internet Service Provider Lag | 3 | 5 | 15 | Check inventory error log for unexpected changes. (IT - Bill)
All Stages | (D/R) Activities/tasks missing from scope | 2 | 7 | 14 | Notify project champion; have relevant party submit change request form. (PM - Nick)
All Stages | (R/T) Staff turnover | 1 | 10 | 10 | Contact project champion (PM - Nick)
All Stages | (PM) Unclear authority | 2 | 5 | 10 | Advise project champion; schedule team meeting to establish clear authority. (PM - Nick)
All Stages | (PM) Lack of communication by PM | 1 | 8 | 8 | Contact project champion. (APM - Jaspreet)
All Stages | (R/T) Lack of communication by team members | 1 | 8 | 8 | Contact project champion. (PM - Nick)
All Stages | (R/T) Low Team Motivation | 2 | 4 | 8 | Organize incentives to raise morale. (PM - Nick)
All Stages | (C) Wrong task is completed by wrong team member | 2 | 3 | 6 | Schedule team meeting to review relevant tasks; review and revise schedule as needed. (PM - Nick)
Risk Categories: | SS- Sponsor Suport ; PS - Project Scope ; PM - Project Manager ; T - Technical ; C - Communication ; R/T - Resources/Team ; D/R - Design/Requirements ; SH - Stakeholders