## Issue Register
ISSUE REGISTER
| Project Name: |  |  | Inventory system for Theater Program
| Project Manager: |  |  | Nick Batista
©
Summary |  |  |  | Description |  |  | Resolution
ID | Date Raised | Raised By | Status | Description of Issue | Impact | Priority | Action | Owner | Outcome | Date for Resolution | Date Resolved
020419a | 2019-02-04 | Bill | Done | The sponsor Liz mentioned about little to no budget for the inventory system | 8 | 10 | Research on initial low budget inventory feasibility solution | Wen, Bill | Update to new issue | 2019-03-08 | 2019-03-08
030819a | 2019-03-08 | Bill | Done | No budget inventory solution is not feasible. Decided to not proceed with build in-house inventory system due to too many unpredictable potential issues and resource constraints. | 10 | 10 | 1. Research on WordPress Inventory solution 2. Research on SalesForce solution 3. Research on feasible hosting service. | 1. Nick Batista 2. Wen Jin 3. Bill Feng | Move on to an alternative solution | 2019-03-11 | 2019-03-11
031119a | 2019-03-11 | Bill | Done | WordPress and SalesForce solution does not work best with our project scope and available resource | 10 | 10 | Decided to research on other inventory solution possibility with a possible demo. | Wen, Bill | Finalized on inventory solution, AssetTiger | 2019-03-12 | 2019-03-12
© 2003 Method123 Ltd. All rights reserved.
KEY
L = Low M = Medium
H = High VH = Very High